## Schedule
Task | Duration | 3月 | [6 empty] | 4月 | [29 empty] | 5月 | [30 empty] | 6月
|  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日 | 月 | 火 | 水 | 木 | 金 | 土 | 日
Purchase Order Management (POM)
Planning | 1 day | bar: 3月 25 月; 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Coding | 14 days | bar: 3月 26 火 to 3月 29 金; 4月 1 月 to 4月 17 水; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Initial Review/Testing | 2 days | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Resolving Issues | 5 days | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Final Review/Testing | 3 days | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Resolving Issues | 3 days | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Production Release | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Purchase Management (PO)
Screen Design Translation to English | 3 days | bar: 3月 25 月 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Planning | 1 day | bar: 3月 25 月; 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Coding | 30 days | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 18 木 to 5月 30 木; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Initial Review/Testing | 2 days | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 5月 31 金 to 6月 3 月; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Resolving Issues | 5 days | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 4 火 to 6月 10 月; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Final Review/Testing | 3 days | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Resolving Issues | 3 days | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
Production Release | bar: 3月 28 木 to 3月 29 金; 4月 6 土 to 4月 7 日; 4月 9 火; 4月 13 土 to 4月 14 日; 4月 20 土 to 4月 21 日; 4月 27 土 to 4月 28 日; 4月 30 火 to 5月 1 水; 5月 4 土 to 5月 5 日; 5月 11 土 to 5月 12 日; 5月 18 土 to 5月 19 日; 5月 25 土 to 5月 26 日; 6月 1 土 to 6月 2 日; 6月 8 土 to 6月 9 日; 6月 12 水; 6月 15 土 to 6月 16 日; 6月 22 土 to 6月 23 日; 6月 29 土 to 6月 30 日
API001
API002
API003
API004
API005
API006
API007
API008
API009
API010
API011
API012
API013
Legends:
Holiday
Weekends
Task Period
Note on AN4: Initial Release Date

## POM
Purchase Order Management
Breakdown of Coding Task | Duration/Days
purchase order list * initial state | 0.5
purchase order list * during the calculation | 0.5
purchase order list * calculation is complete | 3
edit a voucher of purchase orders | 3
pop-up screen for product search | 2
pop-up screen for product list | 3
(supplemenet) a menu for a vouchar of purchase order | 1
add a voucher of purchase orders | 0.5
pop-up screen to download the purchase order | 0.5
Total | 14
Return

## PM
Purchase Management
Breakdown of Coding Task |  | Duration/Days
1 | 【補足】仕入メニュー / [TIP] menu purchase | 0
2 | 仕入伝票起票（発注伝票対応-伝票一覧）/ Input suppliers Purchase voucher (for order document - List of documents) | 3
3 | 仕入伝票起票（発注伝票対応-伝票検索）/ Input suppliers Purchase voucher (for order document - document search) | 2
4 | 仕入伝票起票（発注伝票対応-伝票起票）/Input suppliers Purchase voucher (for order document - Document Purchase) | 2
5 | 仕入伝票起票（商品別対応-商品一覧）/Input suppliers Purchase voucher (for each product - List of products) | 4
6 | 仕入伝票起票（商品別対応-商品検索）/Input suppliers Purchase voucher (for each product - Product Search) | 1
7 | 仕入伝票起票（商品別対応-伝票起票）/Input suppliers Purchase voucher (for each product - Purchase voucher) | 1
8 | 受注伝票（商品検索ポップアップ‐検索）/Sales order (pop-up Product Search - Search) | 0.5
9 | 受注伝票（商品検索ポップアップ‐一覧）/Sales order (pop-up Product Search - List) | 4
10 | 不良品振替伝票起票（商品一覧）/Kihyo defective transfer slip (Product List) | 2
11 | 不良品振替伝票起票（商品検索）/Purchase defective transfer slip (Product Search) | 0.5
12 | 不良品振替伝票起票（起票）/Purchase defective transfer slip (Purchase) | 0.5
13 | 不良品振替伝票検索（伝票一覧）/Document Search transfer defective (list documents) | 2
14 | 不良品振替伝票検索（伝票検索）/Search defective transfer slip (slip Search) | 0.5
15 | 不良品振替伝票検索（伝票）/Search defective transfer slip (slip) | 0.5
16 | 返品伝票起票（商品一覧）/Kihyo credit voucher (list of products) | 0.5
17 | 返品伝票起票（商品検索）/Kihyo credit voucher (Product Search) | 0.5
18 | 返品伝票起票（起票）/Kihyo credit voucher (Kihyo) | 1
19 | 返品伝票検索（伝票一覧）/Search credit voucher (document list) | 1
20 | 返品伝票検索（伝票検索）/Search credit voucher (document search) | 0.5
21 | 返品伝票検索（伝票）/Search credit voucher (voucher) | 1
22 | 【補足】返品伝票修正（伝票メニュー）/[TIP] fix credit voucher (voucher menu) | 0.5
23 | 返品伝票（出力※印刷用）/Credit voucher (for print output ※) | 1.5
Total |  | 30
Return

## POM_long
Purchase Order Management
Breakdown of Coding Task | Duration/Days
purchase order list * initial state | 3
purchase order list * during the calculation
purchase order list * calculation is complete | 5
edit a voucher of purchase orders | 6
pop-up screen for product search | 4
pop-up screen for product list | 6
(supplemenet) a menu for a vouchar of purchase order | 3
add a voucher of purchase orders | 2
pop-up screen to download the purchase order | 2
Total | 31

## PM_long
Purchase Management
Breakdown of Coding Task |  | Duration/Days
1 | 【補足】仕入メニュー / [TIP] menu purchase | 0
2 | 仕入伝票起票（発注伝票対応-伝票一覧）/ Input suppliers Purchase voucher (for order document - List of documents) | 4
3 | 仕入伝票起票（発注伝票対応-伝票検索）/ Input suppliers Purchase voucher (for order document - document search) | 3
4 | 仕入伝票起票（発注伝票対応-伝票起票）/Input suppliers Purchase voucher (for order document - Document Purchase) | 3
5 | 仕入伝票起票（商品別対応-商品一覧）/Input suppliers Purchase voucher (for each product - List of products) | 6
6 | 仕入伝票起票（商品別対応-商品検索）/Input suppliers Purchase voucher (for each product - Product Search) | 2
7 | 仕入伝票起票（商品別対応-伝票起票）/Input suppliers Purchase voucher (for each product - Purchase voucher) | 2
8 | 受注伝票（商品検索ポップアップ‐検索）/Sales order (pop-up Product Search - Search) | 1
9 | 受注伝票（商品検索ポップアップ‐一覧）/Sales order (pop-up Product Search - List) | 6
10 | 不良品振替伝票起票（商品一覧）/Kihyo defective transfer slip (Product List) | 3
11 | 不良品振替伝票起票（商品検索）/Purchase defective transfer slip (Product Search) | 1
12 | 不良品振替伝票起票（起票）/Purchase defective transfer slip (Purchase) | 1
13 | 不良品振替伝票検索（伝票一覧）/Document Search transfer defective (list documents) | 3
14 | 不良品振替伝票検索（伝票検索）/Search defective transfer slip (slip Search) | 1
15 | 不良品振替伝票検索（伝票）/Search defective transfer slip (slip) | 1
16 | 返品伝票起票（商品一覧）/Kihyo credit voucher (list of products) | 3
17 | 返品伝票起票（商品検索）/Kihyo credit voucher (Product Search) | 1
18 | 返品伝票起票（起票）/Kihyo credit voucher (Kihyo) | 2
19 | 返品伝票検索（伝票一覧）/Search credit voucher (document list) | 2
20 | 返品伝票検索（伝票検索）/Search credit voucher (document search) | 1
21 | 返品伝票検索（伝票）/Search credit voucher (voucher) | 2
22 | 【補足】返品伝票修正（伝票メニュー）/[TIP] fix credit voucher (voucher menu) | 1
23 | 返品伝票（出力※印刷用）/Credit voucher (for print output ※) | 2
Total |  | 51